Women’s Dance and Self-Defense for Peace and Empowerment

India

Lewis & Clark College

Miranda Benson & Hillary Patin, USA, Lewis & Clark College

The first goal of the Women’s Dance and Self-Defense for Peace & Empowerment project was to teach women self-defense skills and to inspire the confidence necessary to use them. The second goal was to foster body awareness and gender cooperation in people of all ages in an effort to shift Indian social consciousness to be more women friendly.

Lewis & Clark College donated $2500 to our project. Past Lewis & Clark projects have received similar funding. Anne Green Gilbert’s organization, The Creative Dance Center, also donated $1750. We used Gilbert’s mind-body integration techniques and theories.

Our original project plan involved working with the Yoga Education Training Society (children and their mothers living in slums), Nirman Southpoint School (students grades 1-11 and their female teachers), and Banaras Hindu University (female college students). We planned to teach the children and students dance, and teach the mothers, female teachers, and female college students dance, as well as verbal, mental, and physical self-defense techniques.

Yoga Education Training Society:

We planned on working with children and mothers living in slums through the Yoga Education Training Society (YETS). We prepared two different types of classes: dance for children, and self-defense training and dance for women. Unfortunately, we ended our partnership with this community after two weeks because we felt our project goals would be better met elsewhere. For example, we never saw the advertised women’s group. Instead, a small group of children (between 1 & 12) of a wide age range came to our classes. We not only found ourselves unprepared for the audience we received, but our coordinator was unable to communicate our purpose to them. Poor organization also contributed to confusion for us and for our students; class times were unclear and unreliable. Often we would wait for up to one hour for students to arrive, only to have them leave half an hour later. We thought these issues may have been largely due to language and cultural differences. However, after two weeks of consistent problems and lack of cooperation, we chose to focus our efforts elsewhere. We had negotiated free lodging with YETS for the duration of our project before we arrived in India, and when we stopped teaching classes there, we had to relocate. We found lodging at a hotel closer to Nirman Southpoint School and Banaras Hindu University.

Nirman Southpoint School:

Leaving YETS was a blessing in disguise. Our proposed four classes a week at Nirman Southpoint School (Nirman) turned into nine classes a week. We taught a weekly 45 minute class to almost each individual grade (1, 2-3, 4, 5, 6, 7, 8, 9+11), as well as one weekly 90 minute class to the female teachers. We taught about 120 students, and 25 of their teachers.

We are very satisfied with the implementation of our project with Nirman students. Teaching many grades enabled us to tailor our lesson plans to best fit each age group. We began each class with Anne Gilbert’s BrainDance, followed by some of Gilbert’s dance games to teach dance concepts (rhythm, levels, speed, pathways, shapes, etc.) and to encourage originality and creativity, skills not encouraged at most Indian schools. We used the rest of class time to teach a variety of folk dances, and some other partner dances to the older students. Although we did not plan on focusing on folk dances, we found them to be ideal for gender cooperation and classroom participation for all ages. Our classes culminated into two small, informal performances: one for teachers and parents for Indian Independence Day, and one for fellow classmates. These performances, both requested by Nirman staff, increased self-confidence as well as respect towards others’ hard work.

Unfortunately, we were not as satisfied with the classes taught to Nirman teachers as we were with classes taught to Nirman students. In each weekly class with the female teachers, we spent 60 minutes introducing self-defense skills, and spent 30 minutes introducing dance concepts.

General Nirman Discrepancies:

Classes with the children went well, despite the occasional language barrier. Most of the teachers spoke English well enough to translate to the students if we needed them to; this translation was necessary only a few times with the younger children. The self-defense classes were difficult because of the language barrier; some of the teachers in the class were from Nirman’s rural campus, and thus did not speak hardly any English. Sometimes it was difficult to tell if the teachers were not comfortable discussing the topics we provided, or if they did not understand what we were saying.

Discipline was an issue with the children at Nirman. Our previous exposure to public Indian schools taught us that traditionally, teachers often exercise very strict discipline and punishment with their students. Nirman, being a progressive institution, does not punish their students, an allowance that the students take extra advantage of when being taught by “guest” or international teachers. Thus, students were far more disobedient than we expected. That we do not speak Hindi only proved to be an added hindrance in keeping our students focused.

It was difficult to get the children to dance with the opposite gender. Although we anticipated this, it was an issue that constantly had to be addressed. It became clear that the older the students, the more uncomfortable they were dancing with the other sex. We did see progress over the course of our project, and we believe this is an issue that deserves further attention.

Overall, the project worked well with the children, but not so well with the teachers. There was obvious improvement in body awareness in all ages, and a notable increase in willingness to dance with the opposite gender among the children. Throughout all 8 classes, Nirman teachers seemed to exhibit a lack of interest. Given the enthusiastic response to our workshop at BHU, we can only speculate on the cause of this difference in interest. It is worth noting that both the students and teachers at Nirman did not sign up for our classes voluntarily, unlike Banaras Hindu University participants.

Banaras Hindu University:

Our experience with Banaras Hindu University (BHU) students teaching mainly mental, verbal, and physical self-defense skills surpassed our expectations. Although formalities, such as official registration for our “workshop,” and necessary translation from English to Hindi took up valuable teaching time, the classes were superb. We almost completely cut dance from the workshop as we felt the self-defense portion was more pertinent information to convey. The women engaged in discussion, and practiced physical self-defense moves with more vigor than expected after our experience with Nirman teachers. We also made a connection with BHU and AIPWA, or All India Progressive Women’s Association. Kusum, a volunteer of the Banaras Chapter of AIPWA, came and spoke on the last day of class to show how women are gathering at the grassroots level to create greater social change, a necessary addition to our workshop focusing largely on protecting the individual. We trained two of our student translators to repeat our workshop in January, and left them with our self-defense supplies and information.

We define peace as a state of being in which each individual feels encouraged and safe to express themselves, and in which that expression is respectful, respected, and responded to. Our project contributed to peace by fulfilling our aforementioned goals. Through dance, we promoted proudness of self, awareness of the internal self as well as the self in relation to others. We also fostered self-expression, and acceptance of others’ self-expression through creative dance, something not generally encouraged in Indian schools. According to a woman who took our class, our self-defense program, “provided a place for us to talk about these important issues that we can’t talk about elsewhere. Not even with our mothers or sisters.” It also encouraged self-respect, self-love, intuition, and community. These contributions towards peace are currently short-term effects, which will ripple indefinitely into the future.

“We gave people the tools not only to challenge the status quo, but to defend themselves against the inevitable resistance they will face.” –Hillary Patin

“This experience was exactly what we had hoped for: the opportunity to create a public forum for very real, and highly suppressed, cultural crises.” –Miranda Benson